## Sheet1
2016 Project Budget
| Project: | Assessment Manager
| Designer: | Liam Mills
| Supervisor | Snjezana Soltic
EXPENDITURE
SALARY
| Design charge rate: |  | 15.25 | <---- enter $/hr
|  |  | Budget |  | Actual
|  | Start date | Hours | Cost | Hours | Cost
1 | Initial negotiation |  | 1 | 15.25 | 1 | 15.25
2 | initial plan, budget & contract |  | 4 | 61 | 8 | 122
3 | Client meetings |  | 14.5 | 221.125 | 13 | 198.25
4 | Design of Examinee GUI |  | 17 | 259.25 | 18 | 274.5
5 | Design of Assessment Designer GUI |  | 54 | 823.5 | 24 | 366
6 | Backend programming for Examinee |  | 55 | 838.75 | 33 | 503.25
7 | Backend programming for Assessment Designer |  | 105 | 1601.25 | 142.5 | 2173.125
10 | Preparation of Interim Report |  | 20 | 305 | 10 | 152.5
11 | Preparation of Presentation |  | 21 | 320.25 | 14 | 213.5
12 | Preparation of Final Report |  | 21 | 320.25 | 15 | 228.75
13 |  |  | 312.5 | 4765.625 | 278.5 | 4247.125
14
FINAL QUOTE & PROFIT / (LOSS)
| Overhead allowance: | 50%
| Profit | 40%
Budget
| Estimated Cost before profit: | 7148.4375
| Gross Profit: | 2859.375
| Quoted Price: | 10007.8125