## Sheet1
Semester 2 2016
Outcomes |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14` | Week 15 | TOTALS
1 | Client meetings |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 7
| Actual hours | [15 empty] | 0
2 | Design of Examinee GUI | Week 1: 3; Week 12: 1 | 4
| Actual hours | Week 1: 3 | 3
3 | Design of Assessment Designer GUI | Week 4: 10; Week 8: 10; Week 12: 1 | 21
| Actual hours | Week 4: 5; Week 7: 2; Week 8: 1 | 8
4 | Backend programming for Examinee | Week 1: 10; Week 2: 10; Week 3: 10; Week 12: 5 | 35
| Actual hours | Week 1: 16; Week 2: 10; Week 3: 7 | 33
5 | Backend programming for Assessment Designer | Week 5: 10; Week 6: 10; Week 7: 10; Week 9: 10; Week 10: 10; Week 11: 10; Week 12: 5 | 65
| Actual hours | Week 5: 5; Week 6: 14; Week 7: 13; Week 8: 29; Week 9: 5; Week 10: 18; Week 11: 10.5 | 94.5
6 | Preparation of Presentation | Week 13: 7; Week 14`: 7; Week 15: 7 | 21
| Actual hours | [15 empty] | 0
7 | Preparation of Final Report | Week 13: 7; Week 14`: 7; Week 15: 7 | 21
| Actual hours | [15 empty] | 0
10
11
12